Mobile Application Development Roadmap

.NET MAUI | iOS & Android | October 2026 Phase 7 Update

| 7 Phases Development Phases | Phases 1–6 Complete | Phase 7 0.7.1b Complete | iOS + Android Target Platforms |
| --- | --- | --- | --- |

Confidential — Updated October 2026

# Roadmap Overview

This document defines the development roadmap for the Vitals mobile application through public launch. Phases 1–6 are complete. Phase 7 is active, with the 0.7.1a trial foundation and 0.7.1b household entitlement/authorization foundation completed and production-tested in October 2026.

The sequencing prioritizes user retention first — phases that create a reason to return tomorrow before phases that add clinical sophistication. The clinical visualization engine, which represents the white paper feature set and the primary physician distribution differentiator, is deliberately placed after the core user loop is complete and before authentication and payments.

| Phase | Name | Key Deliverable | Timeline | Status |
| --- | --- | --- | --- | --- |
| 1 | Core Loop Complete | Dashboard screen | Apr–May 2026 | ✅ Complete |
| 2 | Clinical Value Layer | Medications + Care Team | May–Jun 2026 | ✅ Complete |
| 3 | PDF Export on Mobile | Physician-grade PDF | Jun 2026 | ✅ Complete |
| 4 | Clinical Visualization Engine | LOESS + regression + derivatives | Apr–Jun 2026 | ✅ Complete |
| 5 | Authentication & Multi-Patient | User accounts + family tier | Jun 2026 | ✅ Complete |
| 6 | Onboarding Flow | Sample dashboard + setup | Aug–Sep 2026 | ✅ Complete |
| 7 | Entitlements, Store Billing & Launch | Trial + entitlement foundation; store billing | Oct 2026+ | In Progress — 0.7.1b complete |

| Phase 1 | Core Loop Complete | Timeline Apr–May 2026 | Status ✅ Complete |
| --- | --- | --- | --- |

Objective

Close the core usage loop. The user can currently select a patient and enter vitals. Phase 1 is complete when they can also see what they entered — with meaningful context. This is the feature that creates a reason to open the app tomorrow.

Screens to Build

- Dashboard Screen — primary home screen showing:

- Latest vitals reading with timestamp

- 15-day averages for each tracked metric

- Basic trend charts (line graph per vital sign)

- Quick-entry button to log new vitals

- Vitals History Screen — scrollable list of past readings with date/time

Definition of Done

- User opens app and immediately sees their most recent reading and trend

- Charts render correctly on both Android and iOS

- Data persists correctly between sessions

- Navigation between patient selection, vitals input, and dashboard is seamless

Strategic Rationale

Without the dashboard, the app is a data entry form with no feedback loop. Users who enter data and see nothing will not return. The dashboard transforms the app from a logging tool into a health awareness tool — which is the emotional promise Vitals makes on day one.

Dependencies

- Vitals entry screen (complete)

- Patient selection screen (complete)

- FastAPI backend averages endpoints (complete)

- matplotlib trend chart data available via API

| Phase 2 | Clinical Value Layer | Timeline May–Jun 2026 | Status ✅ Complete |
| --- | --- | --- | --- |

Objective

Add the two data modules that transform Vitals from a blood pressure tracker into a caregiver platform: medication management and care team directory. These modules populate the PDF export and are the primary features that differentiate Vitals from every competitor in the market.

Screens to Build

- Medication List Screen — view all medications for selected patient

- Add/Edit Medication Screen — name, dosage, frequency, prescribing physician, pharmacy, start date

- Medication History — track changes over time (critical for medication timeline in clinical visualization)

- Care Team Directory Screen — list of physicians and specialists

- Add/Edit Provider Screen — name, specialty, practice, phone, address, last visit, next visit

Definition of Done

- User can add, edit, and delete medications with full detail

- User can add, edit, and delete care team members

- Data persists correctly and associates correctly with the selected patient

- Medication data is available to the PDF export pipeline

Strategic Rationale

Dr. Warren's requested distribution card cannot be designed until the PDF is complete. The PDF cannot be complete until medication and care team data exist in the app. Phase 2 unblocks Phase 3, which unblocks the physician distribution strategy.

Pending Feature Decisions

- Glucose tracking field (requested by Dr. Warren) — add to vitals input in this phase

- Weight tracking field (requested by Amy RN) — add to vitals input in this phase

- Last Visit / Next Visit fields on provider screen (requested by Amy RN)

| Phase 3 | PDF Export on Mobile | Timeline Jun 2026 | Status ✅ Complete |
| --- | --- | --- | --- |

Objective

Bring the physician-grade PDF export — already validated by six healthcare professionals — to the mobile application. This is the killer feature and the primary physician distribution tool. Dr. Warren cannot hand out distribution cards until the PDF works on mobile.

Features to Build

- PDF generation triggered from mobile app

- Output includes: latest vitals, 15/30/45/60-day averages, basic trend charts, medication list, care team directory with contacts

- Share sheet integration — share PDF via email, Messages, AirDrop, or save to Files

- PDF branded with Vitals logo and vitals-wellness.com

Definition of Done

- User taps 'Generate PDF' and receives a complete clinical summary document

- PDF renders correctly and professionally on all devices

- PDF can be shared directly from the app via native share sheet

- Output is consistent with the PDF already validated by Dr. Warren, Dr. Martinez, and other clinical endorsers

Strategic Rationale

The PDF is what every physician who has seen Vitals has reacted to. It is the feature that gets scanned into official medical charts, shared with colleagues, and described as 'hospital grade.' Without it on mobile, Vitals is just another BP app. With it, Vitals is the tool Dr. Warren hands to her patients.

Distribution Card Dependency

Once Phase 3 is complete, the Dr. Warren distribution card can be designed and printed. The card requires: a working app in the App Store and Google Play, a QR code linking to the 90-day free trial, and the PDF export as the demonstrated value proposition. Phase 3 completion triggers the distribution card sprint.

| Phase 4 | Clinical Visualization Engine | Timeline Jun–Jul 2026 | Status ✅ Complete |
| --- | --- | --- | --- |

Objective

Implement the mathematical visualization layer that elevates Vitals from a well-designed consumer app to a clinically rigorous platform. This is the white paper feature set — the capability that enables physician co-authorship, journal submission, and the physician distribution network.

Mathematical Framework — Four Layers

- Layer 1 — LOESS Smoothing: Locally Weighted Scatterplot Smoothing applied to raw vital sign data. Produces a smooth trend curve that eliminates measurement noise while preserving clinically relevant patterns. Validated by Shaffer et al. (2019) and Koopman et al. (2020).

- Layer 2 — OLS Linear Regression with Statistical Significance: Slope coefficient (mmHg/day), R-squared (trend consistency/variability indicator), p-value (whether trend is statistically significant or noise). Applied across 7, 15, 30, 45, 60-day windows.

- Layer 3 — First and Second Order Derivatives: Finite difference approximations. First derivative = rate of change. Second derivative = acceleration of change. Detects medication losing effectiveness before averages show it.

- Layer 4 — Trapezoidal Integration: Area under the curve = cumulative BP burden over time. More predictive of end-organ damage than average readings alone.

Visual Presentation Layer

- Smoothed LOESS curve overlaid on raw scatter points with confidence interval shading

- Goal range bands: Normal (<120/80 green), Elevated (120-129 yellow), Stage 1 (130-139 orange), Stage 2 (140+ red). ACC/AHA guidelines. Customizable per patient.

- Medication timeline: Horizontal bar chart below the BP chart. Correlates medication changes with BP response.

- Annotations: Date-stamped notes on chart. Patient-entered and auto-generated from medication history.

Patient-Facing Plain Language Layer

- Trend indicator: Directional arrow + color + plain English. 'Your blood pressure has been rising at a statistically significant rate over the past 30 days.'

- Variability indicator: 'Your readings are inconsistent. Try measuring at the same time each day.'

- Momentum indicator: 'Your medication appears to be working better each week.' or 'Your improvement is slowing down.'

- Burden indicator: 'You spent 68% of the past 30 days with systolic blood pressure above 130 mmHg.'

Applicability

All four mathematical layers apply identically to every tracked metric: BP, heart rate, SpO2, temperature, glucose, weight, cognitive state. The engine is built once and scales across all vital signs.

Definition of Done

- Smoothed trend line renders correctly on all chart types

- Regression outputs (slope, R-squared, p-value) calculate correctly and display in plain language

- Goal range bands render correctly and update when customized

- Medication timeline correctly maps to BP chart timeline

- All mathematical outputs match expected values against test data set

| Phase 5 | Authentication & Multi-Patient | Timeline Jul–Aug 2026 | Status ✅ Complete |
| --- | --- | --- | --- |

Objective

Implement user accounts, secure authentication, and multi-patient support. This phase is a prerequisite for taking payments — you cannot charge a subscriber without knowing who they are. Authentication is placed late in the roadmap deliberately: building auth early creates complexity that slows every other phase.

Features to Build

- User registration and login — email/password with email verification

  - ✅ Update: originally flagged as never built (only Google OAuth existed). Now fully implemented — register/login/email-verification endpoints, bcrypt password hashing, an "unverified until confirmed" flow, and a branded verification email (via Resend) and confirmation page matching the vitals-wellness.com site. Login/Sign Up screens' email/password fields are fully functional, not placeholders.

- JWT/bearer token authentication — already designed in MAUI course modules

- SecureStorage for token persistence on device

- Password reset flow

- Account management screen — email, password change, subscription status

- Multi-patient support — Family tier allows up to 5 patients per account

- Patient switching — seamless switch between managed patients in the app

- Data migration — associate existing locally-stored data with new account on first login

Backend Requirements

- User table in PostgreSQL with hashed credentials

- Patient-to-user relationship table — one user can own multiple patient profiles

- API authentication middleware — all endpoints require valid JWT

- DigitalOcean Droplet migration — Pi 3B+ not suitable for paying subscribers. Nginx + FastAPI + PostgreSQL on cloud infrastructure.

- Cross-household data isolation audit — ✅ Complete: discovered and fixed a real cross-account data leak (a second signup's patients were being written into the original household) traced to two root causes — a hardcoded household ID used across most endpoints instead of the authenticated caller's own household, and JWT auth being silently ignored whenever the legacy API key header was also present (which the mobile client always sends). Every patient-scoped endpoint (vitals, medications, doctors, allergies, visits, incidents, notes, user preferences) now verifies the record actually belongs to the caller's household before reading or writing it.

- Session verification — ✅ Complete: a locally-cached JWT no longer implies a valid account — app launch now calls /api/auth/verify to confirm the account still exists server-side before trusting a restored session, closing a gap where a deleted account would still open straight to the Dashboard.

Definition of Done

- User can register, verify email, log in, and log out

- All vitals data correctly associates with authenticated user account

- Family tier allows creation and switching between up to 5 patient profiles

- Token refresh works correctly — user stays logged in across sessions

- DigitalOcean backend live and serving authenticated requests

| Phase 6 | Onboarding Flow | Timeline Aug–Sep 2026 | Status Complete |
| --- | --- | --- | --- |

Objective

Build the first-time user experience that converts trial downloads into habitual daily users. The onboarding flow is not built until Phase 4 because there needs to be something worth onboarding people into — the core loop, clinical data, and PDF export all need to exist first.

Screens to Build

- Welcome Screen — 'Welcome to Vitals. You're about to turn your daily readings into clear, understandable trends.' — ✅ Built

- Purpose Screen — brief explanation of what the app does and why it matters — ✅ Built

- Personalization Screen — 'Who are you tracking for?' (Myself / A family member / Both). Surfaces family plan naturally without a sales pitch — ✅ Built

- Patient Setup Screen (added scope) — collects name, date of birth, and gender for whoever is being tracked (self and/or family member); creates the actual patient record via the household-scoped /api/patients endpoint — ✅ Built

- Sample Dashboard Screen — pre-populated with example data, clearly labeled 'Example'. Shows what the user's dashboard will look like with real data. Built as a guided coach-mark tour over the real dashboard layout rather than a static mockup — ✅ Built

- Vital Preferences Screen (added scope) — choose which vitals beyond blood pressure to track (heart rate, SpO₂, temperature, weight, glucose); same preference keys the real Settings screen uses, so choices made here immediately apply app-wide — ✅ Built

- First Log Prompt — 'Your baseline starts now. Log your first reading.' Includes a Skip option — ✅ Built

- Login Screen (added scope) — email/password, Google sign-in, and native Apple sign-in; all routes use the same post-auth onboarding/session flow and are fully functional — ✅ Built

- Sign Up Screen (added scope) — email/password registration with verification plus Google/Apple sign-up; existing accounts are routed back to the app instead of incorrectly restarting onboarding — ✅ Built

- Apple ID Sign-In/Sign-Up — native AuthenticationServices flow with nonce/state protection, Apple identity-token verification on the API, stable provider user ID mapping, and shared Vitals session handling — ✅ Built

- Household Sharing / Invite — the primary account holder invites a household member by email from Manage Household (Settings); recipient gets a branded email with a short code, redeemed on the new plan-selection screen’s “Join an existing household” option during their own normal sign-up. Invite codes expire in 24 hours and reserve a patient slot against the household’s limit until used or cancelled, so a second person can never join expecting a slot that isn’t actually available. The joining user attaches to an existing patient (with a DOB/gender confirmation step to prevent claiming the wrong person) or creates a new one if slots remain. patient_users now tracks the relationship (self vs. caregiver) between each user and patient — ✅ Built

Known Issues

- Vital preference display consistency (found Sep 12, 2026) — Vital Preferences (Settings) currently only gates the Vitals Entry form. The Dashboard (Latest readings, 15-day averages, charts) and Vitals History do not respect the same preferences: Weight and Blood Glucose are entirely absent from both even when enabled, and Heart Rate/SpO₂/Temperature always display regardless of whether the user has disabled them. Confirmed this is a client-side display gap only — the backend already returns weight and blood_glucose from all three read endpoints (/api/vitals/latest, /api/vitals/history, /api/vitals/averages), so no backend or data changes are needed, only Dashboard/History view and view-model work — ⏳ Not built

Tone & Design Principles

- Calm and supportive — caregivers are already anxious

- No fear-based messaging, no urgency without context, no clinical jargon

- Promise progress, not instant results: 'In a few days you'll see patterns. In two weeks, the full picture.'

- Use 'meaningful' rather than 'accurate' when describing trend data

Notification Strategy — Local Notifications

Phase 6 introduces local push notifications for retention. Implementation uses OS-level scheduled notifications — no background app process required, minimal battery impact.

- Log reminder: Scheduled at time of last entry. If no new log within 24 hours, fire notification.

- Momentum framing: 'Your 7-day trend is building. Log today to keep it going.' Not 'You missed a day.'

- Milestone notifications: 'You've logged 7 days in a row. Your first trend report is ready.'

Definition of Done

- New user completes onboarding in under 2 minutes

- Sample dashboard correctly demonstrates the value of the paid tier

- Personalization selection correctly configures the app for individual vs. caregiver use case

- Local notification scheduling implemented and tested on both platforms

| Phase 7 | Entitlements, Store Billing & Launch | Timeline Oct 2026+ | Status In Progress |
| --- | --- | --- | --- |

Objective

Establish the production commercial-access model before native store purchase integration. Phase 7 is now componentized rather than treated as one large payment sprint: 0.7.1a delivers the one-time household trial, and 0.7.1b delivers the server-authoritative entitlement, patient-capacity, downgrade-preservation, billing-owner, and household-role foundation. Both components are complete and have been exercised against the production API. StoreKit/Google Play purchase plumbing, restore-purchase verification, premium feature gates, and final store submission remain Phase 7 work.

0.7.1a — Trial Foundation — COMPLETE

Implementation delivered

- One-time household Trial: 30 days of full Premium access, no payment method required, and up to 5 patient profiles.

- Onboarding records plan intent (Standard, Family, or Decide Later/Trial) while every new household receives the same full-access Trial window.

- New households persist trial_started_at and trial_ends_at; subscription_status=trial is the access-state source of truth.

- Backward-compatible request normalization retained for earlier onboarding values (individual → standard; free → trial).

- Existing alpha households were intentionally not assigned retroactive expiration dates during migration, preventing accidental lockout of active testers.

- Engineering version: 0.7.1a (store-safe display version remains 0.7.1). Implementation completed in PR #40.

0.7.1a acceptance validation

- Standard onboarding path creates a 30-day Trial household with full trial access and 5-patient capacity.

- Family onboarding path creates the same full Trial while preserving Family as the household plan intent.

- Decide Later creates Trial intent without requiring a payment method or card collection.

- The onboarding flow continues into patient/personalization setup rather than stopping at plan selection.

- Trial state is surfaced through the API contract (subscription status, trial timestamps, patient capacity) and existing household sign-in remains unaffected.

Current commercial model locked for Phase 7

- Trial — one per household; 30 days; full Premium; no payment method; 5 active patient profiles; cannot be restarted.

- Basic — 2 active patient profiles; core vitals/history/medications/care-team access. Medication and provider counts are not capped.

- Standard — 2 patient profiles plus the full Premium clinical feature set; the household owner is the sole household administrator.

- Family — 5 patient profiles plus the same Premium clinical feature set as Standard; delegated household managers are allowed.

- Founder and Beta — permanent complimentary full Premium, unlimited patient capacity, no billing, and no expiration. The tiers remain separate for analytics/admin messaging.

- Premium-only scope includes advanced clinical analysis/graphs, the new PDF, incidents, visits, notes, and other premium clinical modules.

- Mobile MVP billing uses Apple StoreKit on iOS/iPadOS and Google Play Billing on Android. Stripe is removed from the mobile MVP architecture.

- Billing Owner is distinct from Household Owner/Manager. One Apple/Google subscription maps to one Vitals household unless support performs an explicit migration.

- Failed renewal receives a Vitals-managed 5-day courtesy grace period. Failed initial purchase receives no grace. Cancellation preserves Premium until the paid-through date.

0.7.1b — Entitlement & Authorization Foundation — COMPLETE

Implementation delivered

- Household-level entitlement schema and API contract added for owner identity, Billing Owner, billing provider/product, subscription period, grace period, cancellation-at-period-end, and entitlement update timestamp.

- Central entitlement resolver establishes precedence: Founder → Beta → active paid subscription → billing grace → active Trial → Basic.

- Effective patient capacity now follows effective entitlement instead of stale stored values: Basic 2, Standard 2, Trial 5, Family 5, Founder/Beta unlimited.

- Founder and Beta are first-class permanent complimentary tiers with unlimited capacity and no purchase/manage-billing path.

- Over-capacity downgrade preservation added: patient rows and clinical history are never deleted. The household explicitly selects which profiles remain active; unselected profiles are entitlement-locked.

- The MAUI app routes to a dedicated Choose Active Patients screen when a finite plan is over capacity and no valid selection exists. Normal patient navigation filters locked profiles.

- Upgrading capacity automatically restores locked profiles without data restoration or manual unlock SQL. A previous selection is retained for later downgrades.

- Patient creation, invite-slot calculation, and household join capacity all use the same central effective entitlement math.

- Household authorization is server-authoritative: owner identity comes from households.owner_user_id; Basic/Standard are owner-managed; Family permits delegated managers.

- Invite creation/list/cancel and over-capacity patient selection are protected by centralized household-management authorization. Billing authority remains separate.

- 0.7.1b was completed through the entitlement and hardening PR series (#41, #43, #44, #45, #47), with PR #46 correcting the MAUI XAML minimum-height property.

0.7.1b production validation record

- Founder: verified permanent Premium access, unlimited capacity, no billing provider/owner requirement, and no expiration downgrade.

- Beta: verified permanent Premium access and unlimited capacity independently from Founder.

- Basic: verified no Premium access and an effective 2-patient limit.

- Active Trial: verified Premium access and 5-patient capacity.

- Expired Trial: initial test exposed a stale-capacity defect (effective Basic but stored limit 5). The resolver/capacity patch corrected it; retest returned Basic with limit 2.

- Active Standard: verified Premium access with 2-patient capacity.

- Active Family: verified Premium access with 5-patient capacity.

- Active failed-renewal grace: verified Premium remained active during grace, Family capacity remained 5, purchasing was blocked, and the Billing Owner retained billing-management authority.

- Expired grace: verified automatic effective fallback to Basic with Premium disabled and 2-patient capacity.

- Cancellation paid-through: verified cancel_at_period_end does not remove Premium before subscription_ends_at; moving the paid-through date into the past immediately produced Basic fallback.

- Over-capacity paid expiration: with a Family household containing 3 patients, expiration produced effective Basic, limit 2, patient_count 3, and requires_basic_patient_selection=true.

- Capacity enforcement: attempting to create a fourth patient while effective Basic returned the expected plan-limit 403; household status reported zero available slots and can_invite=false.

- Explicit patient selection: the MAUI screen required selection of exactly 2 of 3 patients. After save, entitlement reported active_patient_count=2, locked_patient_count=1, and selection no longer required.

- Locked-profile enforcement: a direct request to the locked patient height-history endpoint returned 403 with the plan-lock message, confirming server-side enforcement rather than UI-only hiding.

- Upgrade restoration: restoring active Family immediately reported all 3 patients active/unlocked and the previously blocked patient endpoint succeeded; no patient row or clinical data restoration was required.

- Repeat downgrade: returning the same household to effective Basic reused the prior 2-patient selection, went directly to the main dashboard, and showed only the 2 active patients without forcing a new selection.

- Owner/manager authorization: the real household owner retained management rights on effective Basic while invite capacity remained independently blocked by the 2-patient limit.

- Basic manager: a dedicated non-owner test user with stored role=manager resolved to can_manage_household=false and received 403 on protected household-management endpoints.

- Family manager: the same user, role, and JWT automatically resolved to can_manage_household=true after Family was restored; invite listing succeeded and two invite slots were available.

- Family member: changing only the test user role to member produced can_manage_household=false and the protected invite endpoint returned 403.

- Standard manager: active Standard correctly disabled delegated management; the manager received the plan-specific owner-only 403 while Premium access remained active.

- Fixture cleanup: Spartan Guy household restored to a consistent active Family state (5-patient capacity, 3 active, 0 effective locks, owner and Billing Owner true); temporary role-test user parked as member.

Security and regression notes

- The patient-lock workflow was validated on a representative patient-scoped clinical endpoint and on normal MAUI patient navigation; a full endpoint-by-endpoint lock audit remains a pre-launch hardening task.

- Cross-household data isolation fixes from Phase 5 remain a non-regression requirement. Selection IDs and all patient/child-record routes must continue to reject records outside the caller household.

- The 0.7.1b tests intentionally exercised production entitlement state transitions by mutating the controlled Spartan Guy fixture; Founder alpha households were not repurposed for destructive entitlement testing.

Remaining Phase 7 Work

- Implement StoreKit purchase/renewal/restore flow on iOS/iPadOS and Google Play Billing purchase/renewal/restore flow on Android.

- Verify Apple transaction data / Google purchase tokens on the backend and safely map each store subscription to one Vitals household.

- Build subscription-management UI for current plan, renewal/paid-through status, cancellation state, upgrade/downgrade, Billing Owner, and Restore Purchases.

- Apply Premium feature gates consistently across advanced analysis/graphs, PDF, incidents, visits, notes, and other premium-only modules while preserving all clinical data on downgrade.

- Complete cross-household and patient-lock regression audit across direct patient/child-record endpoints, including selection-ID rejection tests.

- Complete physical-device billing tests, store listings, production signing/release builds, privacy/terms/support readiness, and final launch submission.

App Store & Google Play Billing / Submission

Current architecture decision: Vitals mobile subscriptions are sold through the platform stores rather than Stripe. The server entitlement model is already designed around Apple/Google billing providers and a distinct Billing Owner; the native purchase and transaction-verification layers are the next implementation step.

Android — Google Play

- Integrate Google Play Billing products for Standard and Family and send purchase tokens to the Vitals API for verification.

- Test initial purchase, renewal, failed renewal/grace, cancellation paid-through behavior, upgrade/downgrade, and Restore Purchases on physical Android devices.

- Complete Play Console production listing, release signing, screenshots, description, age rating, privacy declarations, and staged production rollout.

iOS / iPadOS — App Store

- Integrate StoreKit products for Standard and Family and send signed transaction data to the Vitals API for verification.

- Test initial purchase, renewal, failed renewal/grace, cancellation paid-through behavior, upgrade/downgrade, and Restore Purchases on physical Apple devices.

- Complete App Store Connect listing, production signing/provisioning, screenshots, privacy declarations, and review submission.

Launch Checklist

- Phases 1–6 complete; Phase 7 entitlement foundation (0.7.1a + 0.7.1b) complete and production-tested.

- StoreKit and Google Play Billing purchase/renewal/restore flows verified end-to-end against production-like store test environments.

- Premium gates, downgrade preservation, 5-day renewal grace, paid-through cancellation, and patient-capacity behavior regression-tested on both platforms.

- DigitalOcean production API remains live and sized for initial subscriber load.

- Privacy policy and terms of service published at vitals-wellness.com; support email and account-recovery processes ready.

- Dr. Warren distribution materials and KDP QR-code destinations point to the live store/landing experience.

- Production signing, store metadata, screenshots, age ratings, privacy disclosures, and release notes complete for each launch platform.

Definition of Done

Vitals is available through the intended mobile stores with verified native subscription billing. A new household can complete the one-time Trial, continue on Basic or purchase Standard/Family, retain clinical data through downgrade or billing failure, restore eligible purchases safely, and use the correct patient capacity and household-management permissions throughout the subscription lifecycle.

# Post-Launch Development Priorities

The following features are confirmed for post-launch development, sequenced by clinical impact and subscriber retention value:

| Feature | Rationale | Requested By |
| --- | --- | --- |
| NDC drug database autofill for medication entry | Reduces friction for medication setup | Product roadmap |
| Appointment notifications with Last/Next Visit | Caregiver workflow support | Amy (RN) |
| Firebase Cloud Messaging push notifications | Server-personalized retention messaging | Product roadmap |
| Bluetooth device integration (BP cuffs, glucometers) | Eliminates manual entry friction | Koopman et al. research |
| Cognitive state tracking module | Dementia/TBI caregiver use case | Founder caregiving experience |
| White paper publication | Physician distribution network activation | Dr. Martinez co-authorship target |
| HL7 integration for enterprise licensing | WellMed, Baylor Scott White potential | Long-term enterprise strategy |

# Project Management Notes

## Single Developer Context

This roadmap is built for a single senior developer working on Vitals as a side project alongside full-time employment. Phase durations are estimated conservatively. Workload and caregiving responsibilities are real scheduling variables. The roadmap is designed to be sequential — no phase requires parallel tracks — so that progress is always forward even when velocity varies.

## GitHub Repository Strategy

All Vitals development should be committed to a dedicated private GitHub repository separate from any Pharmacy Unlimited repositories. No Vitals code, architecture, or methodology should touch Pharmacy Unlimited systems or repositories. This is both an IP protection measure and a contractual compliance requirement given the existing NDA and IP assignment clauses.

## Backend Migration Status

DigitalOcean production infrastructure is live and serving authenticated Vitals traffic. The Phase 5/6 migration moved the API off the Raspberry Pi development host and established the cloud deployment path used for the 0.7.1 entitlement tests. Remaining launch work is operational hardening and subscriber-load readiness rather than a first migration.

## The Original September 2026 Constraint

September 2026 was the original hard launch target. Phase 7 expanded from a single payment sprint into a production entitlement architecture with explicit Trial, Basic, Standard, Family, Founder, and Beta states; downgrade preservation; Billing Owner separation; grace/cancellation behavior; and household-role authorization. That foundation moved final store-billing work into October 2026. The priority is now to finish native store billing and launch with entitlement behavior proven under failure, downgrade, and restore scenarios rather than force a stale calendar date.

The strategic business objective remains sustainable recurring revenue and independence. Phase 7 now prioritizes reliable subscription lifecycle behavior, store compliance, and subscriber trust before public launch.

Phase 7 — October 2026.

Vitals — Mobile Application Development Roadmap | Updated October 2026